## 01_Roadmap
Phase | Start Date | Task | Status | End Date | Comments | Documentation Status
Phase 0 | 2026-05-30 | Complete Architecture Audit (Backend, Frontend, DB, Infrastructure) | 100% | 2026-05-30 | Completed | Documented
Phase 0 | 2026-05-30 | Generate Architecture Diagram | 100% | 2026-05-30 | Completed | Documented
Phase 0 | 2026-05-30 | Generate Database ER Diagram | 100% | 2026-05-30 | Completed | Documented
Phase 0 | 2026-05-30 | API Inventory Documentation | 100% | 2026-05-30 | Completed | Documented
Phase 0 | 2026-05-30 | Infrastructure Inventory | 100% | 2026-05-30 | Completed | Documented
Phase 0 | 2026-05-30 | Technical Debt Report | 100% | 2026-05-30 | List all weaknesses | Documented
Phase 0 | 2026-05-30 | Risk Register | 100% | 2026-05-30 | Initial risks identified | Documented
Phase 0 | 2026-05-30 | Production Readiness Assessment | 100% | 2026-05-30 | Baseline measurement | Documented
Phase 1 | TBD | Cloudflare R2 Storage Migration | 0% | TBD | Remove local storage dependency
Phase 1 | TBD | Storage Service Abstraction Layer | 0% | TBD | Future provider switching
Phase 1 | TBD | Signed Upload URLs | 0% | TBD | Secure uploads
Phase 1 | TBD | Signed Download URLs | 0% | TBD | Secure downloads
Phase 1 | TBD | Automatic File Cleanup | 0% | TBD | Cleanup temporary files
Phase 1 | TBD | Redis Installation | 0% | TBD | Queue foundation
Phase 1 | TBD | Redis Queue Setup (RQ) | 0% | TBD | Job processing
Phase 1 | TBD | Worker Architecture | 0% | TBD | Decouple API and rendering
Phase 1 | TBD | Retry Strategy | 0% | TBD | Handle transient failures
Phase 1 | TBD | Dead Letter Queue | 0% | TBD | Failed job storage
Phase 1 | TBD | Job State Machine | 0% | TBD | Recoverable processing
Phase 1 | TBD | Structured Logging | 0% | TBD | JSON logging
Phase 1 | TBD | Configuration Management | 0% | TBD | Dev/Staging/Prod
Phase 1 | TBD | Secrets Management | 0% | TBD | Secure credentials
Phase 2 | TBD | Direct Browser Uploads | 0% | TBD | Remove backend bottleneck
Phase 2 | TBD | WebSocket Infrastructure | 0% | TBD | Real-time progress
Phase 2 | TBD | Real-time Job Tracking | 0% | TBD | Live updates
Phase 2 | TBD | Translation Cache | 0% | TBD | Reduce AI costs
Phase 2 | TBD | User Cache Layer | 0% | TBD | Faster dashboard
Phase 2 | TBD | Credits Cache Layer | 0% | TBD | Reduce DB load
Phase 2 | TBD | Database Index Review | 0% | TBD | Query optimization
Phase 2 | TBD | Slow Query Analysis | 0% | TBD | Identify bottlenecks
Phase 2 | TBD | Connection Pool Tuning | 0% | TBD | Better concurrency
Phase 2 | TBD | Pagination Everywhere | 0% | TBD | Large dataset support
Phase 3 | TBD | Dockerize Backend | 0% | TBD | Environment consistency
Phase 3 | TBD | Dockerize Frontend | 0% | TBD | Environment consistency
Phase 3 | TBD | Production Docker Compose | 0% | TBD | Easier deployments
Phase 3 | TBD | CI Pipeline (GitHub Actions) | 0% | TBD | Automated validation
Phase 3 | TBD | Automated Build Pipeline | 0% | TBD | Deployment readiness
Phase 3 | TBD | Automated Deployment Pipeline | 0% | TBD | Safe releases
Phase 3 | TBD | Environment Promotion Workflow | 0% | TBD | Dev→Staging→Prod
Phase 4 | TBD | Unit Testing Framework | 0% | TBD | Backend tests
Phase 4 | TBD | API Integration Tests | 0% | TBD | Endpoint validation
Phase 4 | TBD | Worker Job Tests | 0% | TBD | Queue reliability
Phase 4 | TBD | Frontend Component Tests | 0% | TBD | UI stability
Phase 4 | TBD | End-to-End Tests | 0% | TBD | User journey testing
Phase 4 | TBD | Payment Flow Tests | 0% | TBD | Revenue protection
Phase 4 | TBD | Regression Test Suite | 0% | TBD | Prevent breakage
Phase 5 | TBD | Dashboard Search | 0% | TBD | Better UX
Phase 5 | TBD | Dashboard Filters | 0% | TBD | Better UX
Phase 5 | TBD | Job History Page | 0% | TBD | Visibility
Phase 5 | TBD | Retry Failed Jobs UI | 0% | TBD | Self-service recovery
Phase 5 | TBD | Notification Center | 0% | TBD | User awareness
Phase 5 | TBD | Email Notifications | 0% | TBD | Job status
Phase 5 | TBD | Admin Dashboard | 0% | TBD | Operations visibility
Phase 5 | TBD | Billing Dashboard | 0% | TBD | Financial visibility
Phase 6 | TBD | Rate Limiting | 0% | TBD | Abuse protection
Phase 6 | TBD | Upload Validation | 0% | TBD | Secure uploads
Phase 6 | TBD | Malware Scanning | 0% | TBD | File security
Phase 6 | TBD | Audit Logging | 0% | TBD | Compliance
Phase 6 | TBD | Database Backup Automation | 0% | TBD | Recovery
Phase 6 | TBD | Storage Backup Automation | 0% | TBD | Recovery
Phase 6 | TBD | Disaster Recovery Runbook | 0% | TBD | Operations
Phase 6 | TBD | Security Headers | 0% | TBD | Web protection
Phase 6 | TBD | Dependency Vulnerability Scanning | 0% | TBD | Supply chain security
Phase 7 | TBD | Sentry Integration | 0% | TBD | Error tracking
Phase 7 | TBD | Metrics Collection | 0% | TBD | Observability
Phase 7 | TBD | Grafana Dashboards | 0% | TBD | Monitoring
Phase 7 | TBD | Alerting System | 0% | TBD | Fast incident response
Phase 7 | TBD | Cost Monitoring Dashboard | 0% | TBD | Profitability tracking
Phase 7 | TBD | AI Usage Monitoring | 0% | TBD | ElevenLabs costs
Phase 8 | TBD | Dedicated Worker Server | 0% | TBD | Isolation
Phase 8 | TBD | Multi-worker Scaling | 0% | TBD | High traffic
Phase 8 | TBD | CDN Integration | 0% | TBD | Global speed
Phase 8 | TBD | FFmpeg Migration | 0% | TBD | Faster rendering
Phase 8 | TBD | Benchmark Testing | 0% | TBD | Capacity planning
Phase 8 | TBD | Load Testing | 0% | TBD | Traffic simulation
Phase 8 | TBD | Stress Testing | 0% | TBD | Failure limits
Phase 9 | TBD | Voice Marketplace | 0% | TBD | Revenue feature
Phase 9 | TBD | Premium Voice Packs | 0% | TBD | Revenue feature
Phase 9 | TBD | Voice Cloning | 0% | TBD | Premium feature
Phase 9 | TBD | API Access | 0% | TBD | B2B revenue
Phase 9 | TBD | Team Workspaces | 0% | TBD | Collaboration
Phase 9 | TBD | White Label Offering | 0% | TBD | Agency market
Phase 10 | TBD | Lip Sync | 0% | TBD | Advanced AI
Phase 10 | TBD | Speaker Detection | 0% | TBD | Quality improvement
Phase 10 | TBD | Emotion Preservation | 0% | TBD | Premium quality
Phase 10 | TBD | Translation Quality Scoring | 0% | TBD | QA automation
Phase 10 | TBD | Subtitle Intelligence | 0% | TBD | Better captions
Phase 11 | TBD | Analytics Dashboard | 0% | TBD | Product insights
Phase 11 | TBD | User Funnel Tracking | 0% | TBD | Conversion optimization
Phase 11 | TBD | Churn Analytics | 0% | TBD | Retention
Phase 11 | TBD | Revenue Analytics | 0% | TBD | Business health
Phase 12 | TBD | Organization Accounts | 0% | TBD | Enterprise
Phase 12 | TBD | SSO Login | 0% | TBD | Enterprise
Phase 12 | TBD | SLA Monitoring | 0% | TBD | Enterprise
Phase 12 | TBD | Enterprise Billing | 0% | TBD | Enterprise
Phase 12 | TBD | Dedicated Infrastructure | 0% | TBD | Enterprise
Phase 14 - Advanced AI Features |  | Automatic subtitle positioning
Phase 14 - Advanced AI Features |  | Lip sync integration
Phase 15 - Enterprise Readiness |  | SSO integration
Phase 15 - Enterprise Readiness |  | Advanced reporting
Phase 15 - Enterprise Readiness |  | SLA monitoring
Phase 15 - Enterprise Readiness |  | Dedicated customer infrastructure options
Phase 15 - Enterprise Readiness |  | Enterprise security audit